## Sheet1
Task Name | Start Date | End Date | Duration | Assigned to | Milestone?
Software Interface | 2019-04-01 | 2019-05-01 | 30 | David
Serial comm. Software subroutine for Romulator | 2019-04-23 | 2019-04-26 | 3 | David
Schematic design review | 2019-04-25 | 2019-04-26 | 1 | David, Thien
Decide on cabling | 2019-04-25 | 2019-04-26 | 1 | David
Gather parts needed | 2019-04-25 | 2019-05-03 | 8 | Biniyam
Design or request info on cable | 2019-04-26 | 2019-05-01 | 5 | David, Thien
Serial comm software subroutine for Arduino | 2019-04-26 | 2019-05-01 | 5 | David, Thien
PCB Design | 2019-04-26 | 2019-05-03 | 7 | Nema, Biniyam
Send for cables or PCB draft adaptors | 2019-05-01 | 2019-05-06 | 5 | David, Thien
Port & chip select software for Arduino | 2019-05-01 | 2019-05-15 | 14 | David, Thien
Send Romulator board for fab | 2019-05-03 | 2019-05-03 | 1 | Nema | Y
Submit complete parts list | 2019-05-03 | 2019-05-03 | 1 | Nema | Y
Send adaptor PCBs for fabrications (if designing) | 2019-05-06 | 2019-05-06 | 1 | Thien | Y
Ensure board fits properly in box | 2019-05-10 | 2019-05-10 | 1 | Thien
Receive board | 2019-05-13 | 2019-05-13 | 1 | Nema | Y
Receive parts | 2019-05-13 | 2019-05-13 | 1 | Biniyam | Y
Inspect board | 2019-05-13 | 2019-05-15 | 2 | David, Nema
Verify compatibility and operability of each component | 2019-05-13 | 2019-05-18 | 5 | Thien, Biniyam
Redesign board (if incorrect) | 2019-05-15 | 2019-05-16 | 1 | Nema
Verify software is correct and complete | 2019-05-15 | 2019-05-20 | 5 | Biniyam
Receive complete cables & adaptors. | 2019-05-16 | 2019-05-16 | 1 | Thien | Y
Refab board (if incorrect) | 2019-05-16 | 2019-05-26 | 10 | Nema
Software corrections and retesting | 2019-05-20 | 2019-05-30 | 10 | David, Thien
Receive new board (if old one was incorrect) | 2019-05-26 | 2019-05-26 | 1 | Nema | Y
Verify new board (if old one was incorrect) | 2019-05-26 | 2019-05-27 | 1 | Biniyam
Assemble parts onto board | 2019-05-27 | 2019-05-30 | 3 | Biniyam
First system test | 2019-05-30 | 2019-05-31 | 1 | Thien
Code Refactoring and Documentation | 2019-05-30 | 2019-06-01 | 2 | David
Final report and documentation | 2019-06-01 | 2019-06-10 | 9 | David
Acceptance Testing | 2019-06-04 | 2019-06-09 | 5 | Biniyam
Place completed board into box | 2019-06-09 | 2019-06-09 | 1 | Thien
Dry run | 2019-06-10 | 2019-06-10 | 1 | All | Y
Rehearsals | 2019-06-12 | 2019-06-12 | 1 | All | Y
Presentation | 2019-06-14 | 2019-06-14 | 1 | All | Y
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0